## 2025_Phantom_Fundraiser
Created At | Completed At | Last Modified | Name | Section/Column | Assignee | Assignee Email | Start Date | Due Date | Tags | Notes | Projects | Parent task | Blocked By (Dependencies) | Blocking (Dependencies)
2024-03-18 |  | 2024-03-18 | Determine raffle items | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 | 2024-09-26 | 2024-09-26 | Create form to collect donation info | DONATIONS/AUCTION | Joan Cadigan | jcadigan@pcefonline.com |  | 2024-09-09 |  |  | 2025 Phantom Fundraiser
2024-03-18 | 2024-09-26 | 2024-09-26 | Create form potential solicitors and donation items. | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Monitor donation/donor list and follow up with volunteers | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Check inventory of card stock for table tents | DONATIONS/AUCTION |  |  |  | 2025-01-07 |  |  | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Contact Best Authentics for sports memorabilia | DONATIONS/AUCTION | Joan Cadigan | jcadigan@pcefonline.com |  | 2025-01-02 |  |  | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Upload supporters/donors into BidPal | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Upload Items into BidPal | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Pair items/create Packages | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Convert remaining Items to Packages | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Set and review Package minimum bids | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Renumber Packages by category | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Plan packaging and photo night | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Upload photos of items | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Edit Items to include gif cert info where needed | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Print Gift Certificates and put in envelopes with Package # | DONATIONS/AUCTION | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 | 2024-10-01 | 2024-10-01 | Design and publish BidPal Giving Center website | GIVING CENTER | Joan Cadigan | jcadigan@pcefonline.com |  | 2024-08-15 |  |  | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Set up tickets and prices in BidPal | GIVING CENTER | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Enter sponsor logos into BidPal | GIVING CENTER | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Enter sponsor logos on website | GIVING CENTER | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Gather all guest info, logos from paid sponsors | GIVING CENTER | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Determine run of show | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Invite Vocal Fusion or other student music group | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Create tables and convey to venue | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Book photographer | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-09-25 | Book DJ | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Book any other vendors (photo booth, etc) | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Determine centerpieces | GENERAL EVENT/VENUE | melissamanzon@icloud.com | melissamanzon@icloud.com |  | 2024-01-16 |  |  | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Reserve vendor meals | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-09-12 | Set a budget | GENERAL EVENT/VENUE | Page Zettlemoyer | pzettlemoyer@pcefonline.com |  | 2024-09-12 |  |  | 2025 Phantom Fundraiser
2024-10-01 |  | 2024-10-01 | Silent slideshow during cocktails | GENERAL EVENT/VENUE | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Review names for name tags | GUESTS | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Create list of builders for name tags | GUESTS | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Print name tags/attach ribbons | GUESTS | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Complete table assignments | GUESTS | [6 empty] | 2025 Phantom Fundraiser
2024-03-18 |  | 2024-03-18 | Note any food allergies or restrictions for venue | GUESTS | [6 empty] | 2025 Phantom Fundraiser
2024-03-25 |  | 2024-08-26 | Review 2024 Phantom Pride | EARLY PLANNING | melissamanzon@icloud.com | melissamanzon@icloud.com |  | 2024-08-26 |  | Look at what got a lot of bids and high bids | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Coordinate teacher volunteers at event? | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Solicit teacher volunteers? | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 | 2024-10-01 | 2024-10-01 | Select School Liaison Chair and a liaison for each school | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Liasons attend Home and School meetings | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Collect donations from schools/teachers, communicate with principals | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Send list of Phantom Pride winners to Principals | SCHOOL LIAISONS | [5 empty] | Send last year's list for inspiration | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Contact Superintendent for approval to contact the building principals for donations | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Put out flyers/posters with "save the date" at Teacher Conferences and winter concerts | SCHOOL LIAISONS | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Invite student groups | SHOWCASE | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Contact Chris Caba/Total Rental to reserve tables, stanchions, easels, etc | SHOWCASE | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Decide how this will look. Will it tie into the Appeal theme? What groups will be represented | SHOWCASE | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Create displays. Make Sponsor SIgns if needed | SHOWCASE | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Permission slips sent to Nicole McClure by Joan for the students | SHOWCASE | [6 empty] | 2025 Phantom Fundraiser
2024-07-29 |  | 2024-07-29 | Print name tags for all We Do This attendees | SHOWCASE | [6 empty] | 2025 Phantom Fundraiser